## Sheet1
BURNDOWN CHART C2 (ADJ BANKING SOFTWARE)
Task | Category | Total Number of Task per Category | Sprint 1 | Sprint 2 | Sprint 3
Test Case, Use Case, and etc. | Documentation | 5 | 4 | 0 | 1 | 1 | 8
System Functionalities | Source Code | 7 | 3 | 4 | 0 | 0
Account Authentications | Database/ Source Code | 4 | 3 | 1 | 0 | 0
Creation of GUI | GUI | 3 | 1 | 2 | 0 | 0
Database Creation | Database | 1 | 0 | 1 | 0 | 0
Unit Testing | Error Checking | 2 | 0 | 2 | 0 | 0
|  | Overall Number of Tasks | Sprint 1 | Sprint 2 | Sprint 3
Actual Effort |  | 20 | 9 | 1 | 0
Ideal Effort |  | 20 | 12 | 6 | 0
ADJ BANKING SOFTWARE
CATEGORY |  | TASKS
Test Case, Use Case, etc. |  | UseCase
Test Case
Burndown
Mock ups
ERD
System Functionalities |  | Open Account
Close Account
View Account
Withdraw
Deposit
Change PIN
Check Balance
Account Authentication |  | Admin Login
Authentication in Closing Account
Authentication in View Account
Card+PIN Authentication (client side)
Creation of GUI |  | Admin GUI
Client GUI
Splash Screen GUI
Database Creation |  | Database Creation
Unit Testing |  | admin
client