## Sheet1
"---------------------------------------------------------------------------------¦¦ PRODUCT BACKLOG ¦¦-----------------------------------------------------------------------"
Title | As a/an | I want to | Priority | Status | Sprint
Administrator Login Function | administrator | be able to login by typing my username and password | 1 | done | 1
Administrator Login Page Error Message | administrator | know that I've done a mistake on logging in by having an error display message when I happen to do so. | 6 | done | 1
Creation of Account | administrator | be able to fulfill one of my duties to create an account for the user/client | 2 | done | 1
Existing account Message | administrator | know if the account I entered was already existing without me having to manually look for it in the data storage. | 7 | done | 1
Closing of Account | administrator | have the means to close an account with the convenience of just typing the account number. | 3 | done | 1
Closing a Non-Existing Account | administrator | be corrected that the account I was closing does not even exist by having an error message flashed before me. | 8 | done | 1
View account Information | administrator | be able to see the account information of a user such as the name, city/address, age, contact number, email address, card and account number and the balance remaining. | 4 | done | 1
Viewing a Non existing Account | administrator | have an error message displayed that the account I want to view does not exist. | 9 | done | 1
Administrator Logout Function | administrator | be at ease that no other person can have my capabilities as the administrator whenever I leave my workstation by having a log out function. | 5 | done | 1
User/Client Login Function | user | login by utilizing the card number and pin number that I have. | 10 | done | 2
User/Client Login Page Error Message | user | know that I've entered a wrong card number or pin number. | 18 | done | 2
User Maximum Login Attempts | user | have a at least three tries only so that my account would be protected if it happens because I was not the one accessing the particular account. | 19 | done | 2
Deposit Function | user | deposit my money with the amount that I will dictate. | 11 | done | 2
New Transaction | user | be able to perform another transaction without having to log in again. | 16 | done | 2
Automatic Session End | user | end the session right after I press cancel when given the choice for a new transaction. | 17 | done | 2
Withdraw Function | user | withdraw my savings by entering the amount I desire. | 12 | done | 2
Withdraw Error Message | user | be informed if the amount I entered is greater than my balance or if it exceeds the limit amount per transaction. | 20 | done | 2
Issuance of Receipt | user | know the updated balance after I withdraw or deposit. | 15 | done | 2
Balance Inquiry Function | user | know my current balance without having to deposit or withdraw. | 13 | done | 2
Ability to Change Pin | user | change the pin number by entering a new one and reentering to confirm the similarity. The password field must be masked. | 14 | done | 2
Error Message on Changing Pin | user | know the error on changing pins whether the new pin entered was the same as the recent pin, there was a missing field, or the reenter is not similar. | 20 | done | 2
Splash Screen | user and admin | see a nice looking splash screen to feel the marketablity of the product. | 21 | done | 2